## Test cases
Test information
Project name : Sweden Wooden sculpture Homepage
Author : Songhei Lee / Developer : Songhei Lee / Tester : Songhei Lee
Version : v 1.0
Test environment
Device 1 : Macbook Air 13"
Device 2 : Samsung laptop NT900X5L
Device 3 : iPhone XS MAX
Device 4 : iPad Air2
Device 5 : LG V30S
Full Test (Function)
No. | Category | Test process | Expect result | Actual result | [7 empty] | Etc
|  |  |  | Device 1 | Device 2 | Device 3 |  | Device 4 |  | Device 5
[6 empty] | Vertical | Horizontal | Vertical | Horizontal | Vertical | Horizontal
1 | Logo image | 1. Look the Logo image by the resolution 2. Click the Logo image | 1. By resolution - Less than 768 px : hide the logo image - More than 768 px : show index.html page 2. The logo image link needs to work on every page. 3. When we click the logo image : show index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
2 | Hamburger Menu | 1. Look Hamburger menu button ty the resolution 2. Click the hamburger menu button | By resolution - More then 768 px : hide the menu button and without any reaction - Less than 768 px : Show the button and the menu works on every page | N/A | N/A | Pass | N/A | Pass | N/A | Pass | Pass
3 | Menu (aside) | 1. Click Home | Show index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Device 3, Device 4 Horizotal mode : indeximg problem
4 |  | 1. Click Information | Show information.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
5 |  | 1. Click Information - Dala horse | Show dalahorse.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
6 |  | 1. Click Information - Rooster | Show rooster.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
7 |  | 1. Click Gallery | Show gallery.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
8 |  | 1. Click Purchase | Show allgoods.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
9 |  | 1. Click Purchase - Dala horse | Show dalahorsegoods.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
10 |  | 1. Click Purchase - Rooster | Show roostergoods.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
11 |  | 1. Click About us | Show aboutus.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
12 |  | 1. Click Our store | Show aboutus.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
13 |  | 1. Click Contact us | Show contactus.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
14 | Information (information.html) | 1. Look the contents | Show a dalahorse image and a rooster image | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
15 |  | 1. Click "Home" on the breadcrumb navigation | Show index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
16 |  | 1. Click the horse image | Shows dalahorse.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
17 |  | 1. Click the rooster image | Shows rooster.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
18 | Dala horse (dalahorse.html) | 1. Look the contents | A dalahorse image and an article | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
19 |  | 1. Click "Home" on the breadcrumb navigation | Show index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
20 |  | 1. Click "Information" on the breadcrumb navigation | Shows information.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
21 | Rooster (rooster.html) | 1. Look the contents | A dalahorse image and an article | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
22 |  | 1. Click "Home" on the breadcrumb navigation | Shows index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
23 |  | 1. Click "Information" on the breadcrumb navigation | Shows information.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
24 | Gallery (gallery.html) | 1. Look the contents 2. Click every image | 1. Shows the 8 images on the page 2. When you click an image, the image will be open on a new window | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
25 |  | 1. Click "Home" on the breadcrumb navigation | Shows index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
26 | Purchase (allgoods.html) | 1. Look the contents | Shows the 6 goods on the page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
27 |  | 1. Click every "sold out" button | No reaction | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
28 |  | 1. Click "Home" on the breadcrumb navigation | Shows index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
29 | Purchase - Dala horse (dalahorsegoods.html) | 1. Look the contents | Shows the 4 goods on the page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
30 |  | 1. Click every sold out button | No reaction | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
31 |  | 1. Click "Home" on the breadcrumb navigation | Shows index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
32 |  | 1. Click "Purchase" on the breadcrumb navigation | Shows allgoods.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
33 | Purchase - Rooster (roostergoods.html) | 1. Look the contents | Shows the 2 goods on the page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
34 |  | 1. Click every sold out button | No reaction | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
35 |  | 1. Click "Home" on the breadcrumb navigation | Shows index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
36 |  | 1. Click "Purchase" on the breadcrumb navigation | Shows allgoods.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
37 | About us (aboutus.html) | 1. Look the contents | Shows contact information, a map image, 4 flags image and a link of "Message us!" | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
38 |  | 1. Click "Home" on the breadcrumb navigation | Shows index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
39 |  | 1. Click "About us" on the breadcrumb navigation | Shows aboutus.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
40 |  | 1. Click "Message us!" link | Shows contactus.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
41 | Our store (aboutus.html) | 1. Look the contents | Shows the contact information, a map image, 4 flags image and a link as "Message us!" | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
42 |  | 1. Click "Home" on the breadcrumb navigation | Shows index.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
43 |  | 1. Click "About us" on the breadcrumb navigation | Shows aboutus.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
44 |  | 1. Click "Message us!" link | Shows contactus.html page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
45 | Contact us (contactus.html) | 1. Look the contents | Shows a form | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
46 |  | 1. Click and select an item on the subject list 2. Input text on Name 3. Input text on E-mail 4. Click and select an item on the language list 5. Input text on Telephone 6. Input text on Message | 1. Subject - List: General, Purchase, Cooperation, Other - Disabled "Please select a type of subject." 2. Name: Some text can be input 3. E-mail: Some text can be input 4. Language - List: English, Swedish, Korean, Japanese - Disabled "Please select your preferred language." 5. Telephone: Some text can be input 6. Message: Some text can be input | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
47 |  | 1. Don't select or input an item | 1. Subject: A selection is required 2. Name: Input text is required 3. E-mail: Input text with "@" is required 4. Language: A selection is not required 5. Telephone: Input text is not required 6. Message: Some text is required | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
48 |  | 1. Select or input on any an item 2. Click "Reset" button | Every item will be returned to the initial status | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
49 |  | 1. Fill out every item 2. Click "Send" button | Shows Codeintitue formdump page with the items which I have input | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
50 | Footer | 1. Click the 4 social media icons | 1. Facebook icon: Open "https://www.facebook.com/ss831" on a new window 2. LinkedIn icon: Open "https://www.linkedin.com/in/songhei-lee-a7ba04139/" on a new window 3. Instagram icon: Open "https://www.instagram.com/ss831_/" on a new window 4. Youtube icon: Open "https://www.youtube.com/results?search_query=dala+horse" on a new window 5. Every icon works on every page | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass

## Bug report
ID | Status | Severity | Model | OS | Browser | procedure | Defect | Comment | Capture file | Tester | Detected Date | Fixed Comment | Developer | Tester Confirm
1 | New | B | iPhone XS MAX, iPad Air 2 | iOS 13.3.1 | Safari | 1. Go index.html | The resolution of the image looks different from the original ratio. | The image ratio is always same. | Refer [bugs capture] sheet : Cap1, Cap2 | Songhei Lee | 2020.03.13 |  | Songhei Lee

## Bugs capture
Cap 1 : On iPhone Xs Max | Cap 2 : On iPad Air 2

## Device specs
| Device 1 | Device 2 | Device 3 | Device 4 | Device 5
Model Name | Macboor Air 13" | NT900X5W | iPhone Xs Max | iPad Air 2 | LG V30S (LG-H930)
OS | macOS Catalina 10.15.3 | Windows 10 Home 10.0.18362 | iOS 13.3.1 | iOS 13.3.1 | Android 9
CPU | Intel core i5 1.6GHz Dual-Core | Intel core i5-7200 2.50 GHz Dual core | Apple A12 Bionic | 1.5GHz tri-core 64-bit ARMv8-A "Typhoon" | Qualcomm Snapdragon 835
RAM | 4 GB | 8 GB | 4 GB | 2 GB | 6 GB
Graphics | Intel HD Graphics 6000 | Intel HD Graphics 620 | APPLE G11P | PowerVR GXA6850 | Qualcomm Adreno 540
Browser | Safari 13.0.5 (15608.5.11) | Chrome 80.0.3987.132 | Safari | Safari | Chrome 80.0.3987.132